## Carryforward Task
SRNo | Milestone | Project | TaskId | Task Name | Task Status | Assigned | Reason to Carryforward | Git Link
1 | Goal_Digger_15062023 | CPOS_WEB_Angular | #376 | Issue : Request reports : UI Total is not match with Excel total | Open | Pankaj Motwani | Need to rectify other character which are taking space, tab or next line that's why it might take some more time
2 | Goal_Digger_15062023 | B2B_Admin_Portal | #16 | US: Admin: Catalogue Master: Detail Page: Catalogue Level Selection | Open | Viraj Pansara | hasmukh sir is working on the level selection component.
3 | Goal_Digger_15062023 | zota-pos-framework | #368 | US: Prior intimation of software version update for uninterruptible service | Open | Mayur | Support task
4 | Goal_Digger_15062023 | B2B_Admin_Portal | #5 | US: Admin: Item Master: Item Detail Page: Item Image | Open | Viraj Pansara | Need to discuss with hasmukh bhai and dhaval bhai
5 | Goal_Digger_15062023 | CPOS_WEB_Angular | #352 | US: Scheme Master New - All schemes configuration with checkbox "Scheme Mandatory" for POS scheme billing | Testing | Nilesh | Have to perform some scenarios and also regression testing is in progress for POS version 1.0.40
6 | Goal_Digger_15062023 | zota-pos-framework | #434 | US: Sales Invoice - Change Requirement to Generate Sales Invoice without Scheme | Testing | Nilesh | Have to perform some scenarios and also regression testing is in progress for POS version 1.0.40
7 | Goal_Digger_15062023 | CPOS_WEB_Angular | #389 | Issue : Change history page is displaying on Login page after session time out for Scheme master and Return policy | Donig | Nidhi | yesterday this task added in milestone.
8 | Goal_Digger_15062023 | B2B_Admin_Portal | #14 | US: Admin: Catalogue Master: List Page | Open | Viraj Pansara | testing of category list done then start working on this task as per discussion with hasmukh sir
9 | Goal_Digger_15062023 | B2B_Admin_Portal | #30 | US: Admin: Banner Master: Listing Page | Open | Viraj Pansara | testing of category list done then start working on this task as per discussion with hasmukh sir
10 | Goal_Digger_15062023 | B2B_Admin_Portal | #32 | US: Admin: Deals & Offer Master: List Page | Open | VIraj Pansara | testing of category list done then start working on this task as per discussion with hasmukh sir
11 | Goal_Digger_15062023 | zota-pos-framework | #408 | Issue : Sales Return - Unhandled Exception Error | Open | Tushar | task is started today.
12 | Goal_Digger_15062023 | B2B_Admin_Portal | #11 | US: Admin: Category Master: List Page | Doing | VIraj Pansara | testing of category list done then start working on this task as per discussion with hasmukh sir
13 | Goal_Digger_15062023 | B2B_Admin_Portal | #10 | US: Admin: Category Master: Detail Page | Doing | Nitish Kumar Singh | I have started this work , Image has been broking while we click on edit or view button.
14 | Goal_Digger_15062023 | Store Execution | #378 | IssueIssue : Notification List - Based on the User wise roles and rights notification is not working | Doing | Amruta | As per discussion today with @ethics.hardik.shah ,we have to change in STAGE lable for DL_APplyDate
15 | Goal_Digger_15062023 | Store Execution | #390 | Issue 1 : DL Approval notification is visible even after DL is approved | Doing | Amruta | As per discussion today with @ethics.hardik.shah ,we have to change in STAGE lable for DL_APplyDate
16 | Goal_Digger_15062023 | Vendor Portal | #28 | IssueIssue : Barcode Pattern Product Mapping List showing blank and product is not showing for print barcode in Live | Open | Amruta | Due to RnD of HTML to PDF work, will do next in next milestone
17 | Goal_Digger_15062023 | Vendor Portal | #15 | Testing: Adhoc Testing of Overall Vendor Portal | Doing | Amruta | Due to RnD of HTML to PDF work, will do next in next milestone
18 | Goal_Digger_15062023 | B2B_Admin_Portal | #31 | US: Admin: Banner Master: Detail Page | Testing | Komal | Have to perform some scenarios in Banner Level section
19 | Goal_Digger_15062023 | zota-pos-framework | #492 | Regression Testing : Release verison - POS (1.0.40) | Testing | Nilesh | Request report functionality bug is pending and added another tasks for release so currently testing is in progress
1 | Goal_Digger_29062023 | B2B_Admin_Portal | #17 | US: Admin: Catalogue Master: Catalogue Item Mapping Page | Open | Viraj Pansara | Add this Task in the milestone At date 11/07/2023.
2 | Goal_Digger_29062023 | CPOS_WEB_Angular | #239 | Issue : CPOS - User is able to "Save&Continue" even when rights for the same is not assigned to respective User | Doing | Pankaj Motwani | Need to carry forward beacuse there is some confusion from my side as data is been feteched from multiple table
3 | Goal_Digger_29062023 | CPOS_WEB_Angular | #385 | CPOS - User List - User is not able to Export File | Open | Pankaj Motwani | Gave For Conformation to deval bhai but returned bug after conformation of rakesh
5 | Goal_Digger_29062023 | CPOS_WEB_Angular | #399 | Issue : Number doesn't changed after click on Next Page button in Admin > User List | QA | Nidhi Garala | Need to Carry Forward becuase On 11-07-2023 evening this task was added in milestone
6 | Goal_Digger_29062023 | CPOS_WEB_Angular | #356 | CPOS Live Issue : Request reports | QA | Nilesh Patel | This Issue will be tested after CPOS Release
7 | Goal_Digger_29062023 | zota-pos-framework | #4 | DI/POS: Account-> Bank -> Entry Form: The Excess Amount should be displayed as Credit | Open | Tushar Prajapti
8 | Goal_Digger_29062023 | B2B_Admin_Portal | #30 | US: Admin: Banner Master: Listing Page | Doing | Viraj Pansara | I am Stuck in Ekatva Task for 3 days
9 | Goal_Digger_29062023 | B2B_Admin_Portal | #31 | US: Admin: Banner Master: Detail Page | Doing | Viraj Pansara | I am Stuck in Ekatva Task for 3 days
10 | Goal_Digger_29062023 | B2B_Admin_Portal | #32 | US: Admin: Deals & Offer Master: List Page | Doing | Viraj Pansara | I am Stuck in Ekatva Task for 3 days
11 | Goal_Digger_29062023 | B2B_Admin_Portal | #5 | US: Admin: Item Master: Item Detail Page: Item Image | Doing | Viraj Pansara
1 | Goal_digger_13072023 | CPOS_WEB_Angular | #397 | POC : Store STOCK Sync ON CPOS | Open | Pankaj Motwani | Need to discuss my analysis and then need to start working on same
2 | Goal_digger_13072023 | CPOS_WEB_Angular | #356 | CPOS Live Issue : Request reports | QA | Nilesh Patel | This Issue will be tested after CPOS Release
3 | Goal_digger_13072023 | Zota_POS_framework | #517 | US : Software Version Update for Network Connected Systems | Doing | Mayur | This Task not completed due to support Activity
4 | Goal_digger_13072023 | Cpos_WEB_Angular | #368 | US : Auto Store Creation in Odoo | Doing | Pankaj Motwani | Took long time because I was purely dependent on Odoo guys for saving data in postgreSql
5 | Goal_digger_13072023 | Cpos_WEB_Angular | #387 | US: Notification Master (Add) - New Requirement | Doing | Nidhi Garala | Nedd to carry forward because another unplanned task related to cPOS live was done by me and some times spend on scheme report Query analysis. in this task attachment development is there , it s time taking for me.
6 | Goal_digger_13072023 | zota-pos-framework | #520 | Issue : Bank / Cash receipt should have created if credit note already created | Doing | Tushar Prajapti | Need to carry forward because discussion is running with Paresh sir.
7 | Goal_digger_13072023 | Cpos_WEB_Angular | #416 | Training : CPOS Understanding | Doing | Tushar Prajapti | Need to carry forward because Understanding is running
8 | Goal_digger_13072023 | B2B_Admin_Portal | #17 | US: Admin: Catalogue Master: Catalogue Item Mapping Page | Open | viraj Pansara | Update US from BA
9 | Goal_digger_13072023 | B2B_Admin_Portal | #32 | US: Admin: Deals & Offer Master: List Page | onHold | viraj Pansara | Deatil Page devplopent is Not done 100%
10 | Goal_digger_13072023 | Cpos_WEB_Angular | #378 | Notification List - Based on the User wise roles and rights notification is not working | QA | Komal | QA Member is on Unplanned (Sick) Leave since last 2 days. We have tried to complete this but unable to do because of other B2B US.
11 | Goal_digger_13072023 | Cpos_WEB_Angular | #414 | US: CPOS: Report: Changes in Store Execution Tracker Report | QA | Komal | QA Member is on Unplanned (Sick) Leave since last 2 days. We have tried to complete this but unable to do because of other B2B US.
12 | Goal_digger_13072023 | B2B_Admin_Portal | #5 | US: Admin: Item Master: Item Detail Page: Item Image | QA | Komal | QA Member is on Unplanned (Sick) Leave since last 2 days. We have tried to complete this but unable to do because of other B2B US.
13 | Goal_digger_13072023 | Vendor-portal_WEB_Angular | #33 | US: Barcode --> Barcode Print : Searchable dropdown for "Vendor" Selection | open | Ashish | Need to carry forward because discussion is running with Amruta ma'am.
1 | Goal_digger_27072023 | CPOS_WEB_Angular | #400 | US: GST Reports --> GST Sales Report | Doing | Pankaj Motwani | Worked on analysis as well as started working on same as need to gather bits from pos which are responsible for delay
2 | Goal_digger_27072023 | CPOS_WEB_Angular | #397 | POC : Store STOCK Sync ON CPOS | Open | Pankaj Motwani | Worked on analysis but development doesn't fitted against requirement because it might create issue related to space on cpos and other challanges too
3 | Goal_digger_27072023 | Cpos_WEB_Angular | #416 | Training : CPOS Understanding | Doing | Tushar Prajapti | Need to carry forward because need more Understanding
4 | Goal_digger_27072023 | B2B_Admin_Portal | #5 | US: Admin: Item Master: Item Detail Page: Item Image | Doing | Viraj Pansara | Need to carry forward because US:145 Is Related to this US And US:145 Assign to me At date:08/08/2023.
5 | Goal_digger_27072023 | Zota_POS_framework | #444 | US: Notifications (Badge and Popup) | Doing | Nidhi Garala | Need to carry forward bcoz notification task was little bit stranger for me
6 | Goal_digger_27072023 | B2B_Admin_Portal | #17 | US: Admin: Catalogue Master: Catalogue Item Mapping Page | Open | Viraj Pansara | need to discuss the existing functionality of this US with @hasmukh sir.
7 | Goal_digger_27072023 | B2B_Admin_Portal | #39 | US: Admin: Home Page Mobile: Detail Page: Basic Information | Doing | Nitish kumar singh | This task add yesterday(07/08/2023) in Milestone , and this task is R&D part.
8 | Goal_digger_27072023 | Vendor-portal_WEB_Angular | #35 | Issue 9: Image doesn't displaying after selecting while making ASN | Doing | Ashish kumar | this task is R&D part because new functionality is discussed with parimal sir and amruta ma'am
9 | Hulk_270723[.NET] | pos_dotnet | #418 | Issue : LS00055 : Need to set up E-Invoice and E-Way Bill credentials. | Doing | Pankaj Motwani | Assigned task from rohit sir and need to complete on priority as customer need to start working on same
10 | Goal_digger_27072023 | CPOS_WEB_Angular | #430 | US: GST Reports --> GST Sales Return Report | Open | Pankaj Motwani | Because of other prioroty task need to carryforward this task
11 | Goal_digger_27072023 | CPOS_WEB_Angular | #378 | Issue : Notification List - Based on the User wise roles and rights notification is not working | open | Amruta Salvi | Need to Carry forward...as issue assigned yesterday and working on other priority project
12 | Goal_digger_27072023 | Vendor-portal_WEB_Angular | #44 | Issue : All Search fields are not working in Barcode Pattern Product Mapping List | Doing | Amruta Salvi | Except "IsActive" search scenario all are working, carry forward task to next milestone
1 | Goal_digger_100823 | B2B_Admin_Portal | #17 | US: Admin: Catalogue Master: Catalogue Item Mapping Page | Open | Viraj Pansara | need to discuss the existing functionality of this US with @hasmukh sir.
2 | Goal_digger_100823 | B2B_Admin_Portal | #5 | US: Admin: Item Master: Item Detail Page: Item Image | QA | Viraj Pansara | When All Current devlopment has been complete at Our side and Mobile side tthen Assign to QA
3 | Goal_digger_100823 | B2B_Admin_Portal | #145 | US: Admin: Item Master: Item Image: Upload Image Functionality | QA | Viraj Pansara | When All Current devlopment has been complete at Our side and Mobile side tthen Assign to QA
4 | Goal_digger_100823 | B2B_API_DotNetCore | #43 | US: API: Admin: Store Management: Registration Approval: Detail Page | Doing | Viraj Pansara | Devploment is done.
1 | Goal_digger_100823 | Home Page Mobile | #39 | Home Page Mobile: Detail Page: Basic Information | Open | Nitish Kumar Singh | Changes in user Story According to Development.
2 | Goal_digger_100823 | CPOS_WEB_Angular | #423 | US: Forgot Password functionality | Doing | Ashish kumar | some functionality is of R&D part
1 | Goal_digger_240823[.NET] | ZOTA DPOS | #21 | US: Rates Calculation Changes | Doing | Pankaj Motwani | Due to another task including L3 Support as well as analysis,development in einvoice irn generation
2 | Goal_digger_240823[.NET] | CPOS_WEB_Angular | #218 | US: Scheme Master New - Required Changes in Scheme "Free Material on Bill Value" | Doing | Pankaj Motwani | E-way bill gap from alankit as well as balaji mariline pvt ltd
3 | Goal_digger_240823[.NET] | CPOS_WEB_Angular | #433 | US: GST Reports --> GST HSN Report | QA | Tushar Prajapti | Need to Carry forward...as issue assigned today(20-09-2023)
4 | Goal_digger_240823[.NET] | CPOS_WEB_Angular | #434 | US: GST Reports --> GST Docs Report | QA | Tushar Prajapti | Need to Carry forward...as issue assigned today(20-09-2023)
5 | Goal_digger_080923[.NET] | Zota_Dpos_Framework | #180 | Issue : DPOS : Purchase Invoice - want to Sales rate column editable | Doing | Tushar Prajapti | Need to Carry forward...as yesterday(20-09-2023) sync is not work so i nead time to solve this
6 | Goal_digger_080923[.NET] | CPOS_WEB_Angular | #528 | Issue: MB not displaying after file size in Notification master add page | QA | Tushar Prajapti | Need to Carry forward...as issue assigned today(20-09-2023)
1 | Goal_digger_080923[.NET] | B2B_Admin_Portal | #145 | US: Admin: Item Master: Item Image: Upload Image Functionality | QA | Viraj Pansara | When All Current devlopment has been complete at Our side and Mobile side tthen Assign to QA
2 | Goal_digger_080923[.NET] | B2B_Admin_Portal | #5 | US: Admin: Item Master: Item Detail Page: Item Image | QA | Viraj Pansra | When All Current devlopment has been complete at Our side and Mobile side tthen Assign to QA
3 | Goal_digger_080923[.NET] | Zee POS | #180 | Issue : Cpos Store stock Data does not matched with Pos Store Stock Reports. | Doing | Mayur | Pending Due to Other P1 Support task
1 | Goal_digger_210923[.NET] | CPOS_WEB_Angular | #477 | US: Scheme Master Report change (Free Material on Bill Value) | Doing | Tushar Prajapti | Need to Carry forward...as Dynamic Query Execution Supports Only 8000 Character.Need to search for another alternative to support more characters and max is also taking 8000 character not more than that.
2 | Goal_digger_210923[.NET] | CPOS_WEB_Angular | #510 | US: Scheme Master Report change (Discount % on Bill Value) | Open | Tushar Prajapti | Need to Carry forward...as Dynamic Query Execution Supports Only 8000 Character.Need to search for another alternative to support more characters and max is also taking 8000 character not more than that.
3 | Goal_digger_210923[.NET] | CPOS_WEB_Angular | #532 | Issue : Data Mismatch for all GST Reports with POS report | Doing | Pankaj Motwani | other task came in between related to gst report as well as first billing date along with balaji eway bill task
4 | Goal_digger_210923[.NET] | CPOS_WEB_Angular | #216 | US: Sales Invoice - Required Changes in Invoice process to apply scheme "Free Material on Bill Value" | Doing | Pankaj Motwani | other task came in between related to gst report as well as first billing date along with balaji eway bill task
5 | Goal_digger_210923[.NET] | B2B Admin Panel | #6 | US: Admin: Item Master: Item Detail Page: Rate: Rate Slab Form | QA | Viraj Pansara | This Task will be carried forward into next milestone because milestone add ad date:29/09/2023 And also busy in Ekatva Budget task.
6 | Goal_digger_210923[.NET] | zota-pos-framework | #619 | Testing : Regression Testing : Release No.: 01_102023 | Testing | Nilesh
7 | Goal_digger_210923[.NET] | CPOS_WEB_Angular | #536 | Testing : Regression Testing : Release No.: 01_102023 | Testing | Nilesh
8 | Goal_digger_210923[.NET] | B2B Admin Panel | #225 | suggestion: Buttons is image section looking disable. | QA | Viraj Pansara | The task Is done But not marge in the Staging Server.
9 | Goal_digger_210923[.NET] | zota-pos-framework | #472 | US: POS - Inactive Customers Report (Nill Sale Report) | Doing | Ashish kumar | Not completely familier with Pos so need to go through the codes to completely understand the flow of the Application.
1 | Goal_digger_051023[.NET] | cpos_web_angular | #449 | US: Reports --> Batch wise Sale Report (Tertiary) | Doing | Pankaj Motwani | Due to another task came in between like e-way bill, other issue from live cpos side
1 | Goal_digger_191023[.NET] | cpos_web_angular | #555 | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/555 | Doing | Pankaj Motwani | As, current project is new to me so, need to understand and work accordingly
2 | Goal_digger_191023[.NET] | cpos_web_angular | #561 | Issue:CPOS: All : requested report :Request report not downloaded from many days | QA | Nilesh | This Issue will be tested after CPOS Release.
3 | Goal_digger_191023[.NET] | ZEELAB_WEB_Angular | #31 | US: CFA Stock Report | Open | Tushar Prajapati | Due to GST SSRS Report work, will do next in next milestone
4 | Goal_digger_191023[.NET] | B2B Admin Panel | #17 | US: Admin: Catalogue Master: Catalogue Item Mapping Page | QA | Deepak Pant | Due to the Priority to change the UI Of the B2B Admin Panel.
5 | Goal_digger_191023[.NET] | B2B Admin Panel | #32 | US: Admin: Deals & Offer Master: List Page | QA | Deepak Pant | Due to the Priority to change the UI Of the B2B Admin Panel.
6 | Goal_digger_191023[.NET] | cpos_web_angular | #509 | Suggestion: Return policy list page should display after click on Save button | Open | Paresh Patel | Due to Other Priority Task of SSRS Report Not able to complete this task, So need to carry forward this task.
7 | Goal_digger_191023[.NET] | cpos_web_angular | #513 | US: Scheme Master Report change (Combo Scheme) | Open | Paresh Patel | Due to Other Priority Task of SSRS Report Not able to complete this task, So need to carry forward this task.
8 | Goal_digger_191023[.NET] | cpos_web_angular | #571 | US : GST Reports in SSRS Report | QA | Tushar Prajapati
1 | Goal_digger_021123[.NET] | cpos_web_angular | #583 | US : Auto Store Creation in Odoo via consuming odoo API | Discussion | Pankaj Motwani | Need to ask mam in which other area sms possiblity is there other than five area + one for otp | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/583
2 | Goal_digger_021123[.NET] | cpos_web_angular | #571 | US : GST Reports in SSRS Report | Testing | Tushar Prajapati
3 | GOal_digger_021123[.NET] | cpos_web_angular | #593 | Issue : GST report - GST Sale Return report - Disc. Value display in R.off column | Done | Pankaj Motwani | Once merge request will be done will able to resolve this issue
4 | Goal_digger_021123[.NET] | cpos_web_angular | #590 | US: Sales Return without Tax report - Add "Discount" column | Doing | Pankaj Motwani | As, Sales Return area issue has been resolved but new bug assied which was previously persistant but now came into picture as tested functionality related to sales return without taxation for debit note, credit note
5 | Goal_digger_021123[.NET] | cpos_web_angular | #571 | US : GST Reports in SSRS Report | Testing | Tushar Prajapati | Data missed matche | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/571
6 | Goal_digger_021123[.NET] | cpos_web_angular | #513 | US: Scheme Master Report change (Combo Scheme) | OnHold | Tushar Prajapati | Due to Other Priority Task of SSRS Report Not able to complete this task, So need to carry forward this task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/513
1 | Goal_digger_281223[.NET] | cpos_web_angular | #568 | Issue : All state state are removed from UI and other state are displaying as selected as ticked if user select all state and click on select all button after search particular state | Open | Tushar Prajapati | Due to Other Priority Task of pos issue Not able to complete this task, So need to carry forward this task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/568
2 | Goal_digger_281223[.NET] | cpos_web_angular | #682 | Issue 2: Select all check box is displaying as ticked if all store category are not selected in GST Report | Open | Tushar Prajapati | Due to Other Priority Task of pos issue Not able to complete this task, So need to carry forward this task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/work_items/682
3 | Goal_digger_281223[.NET] | cpos_web_angular | #681 | Issue 1: Select all check box is displaying as ticked if all store category are not selected in Return policy | Open | Tushar Prajapati | Due to Other Priority Task of pos issue Not able to complete this task, So need to carry forward this task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/work_items/681
4 | Goal_digger_281223[.NET] | zota-pos-framework | #715 | Issue 3: Scheme return is not working properly if multiple schemes are applied | Doing | Tushar Prajapati | This task Assignee yesterday(11/01/2023). | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota-pos-framework/-/work_items/715
1 | Goal_digger_080224[.NET] | cpos_web_angular | #568 | Issue : All state state are removed from UI and other state are displaying as selected as ticked if user select all state and click on select all button after search particular state | Open | Tushar Prajapati | Due to Other Priority Task of .net core conversion Not able to complete this task, So need to carry forward this task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/568
1 | Goal_digger_220224[.NET] | cpos_web_angular | #727 | Issue : Displaying error message after selecting all state, Store Category and Store code in Order & Stock assessment report in Staging and Live. | Open | Tushar Prajapati | Due to Other Priority Task Not able to complete this task, So need to carry forward this task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/727
1 | Goal_digger_070324[.NET] | Kendriya Bhandar Grocery Pos_framework | #1 | US: Kendriya Bhandar (Grocery) - Theme implementation | QA | Tushar Prajapati | Development is Done Pending For CPOS. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/kendriya-bhandar/grocery/pos_framework/-/issues/1
2 | Goal_digger_070324[.NET] | Kendriya Bhandar Grocery Cpos_web_angular | #1 | US: Kendriya Bhandar (Grocery) - Theme implementation & Hosting | QA | Tushar Prajapati | Development is Done Pending deployment and hosting API. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/kendriya-bhandar/grocery/cpos_web_angular/-/issues/1
3 | Goal_digger_070324[.NET] | ZEELAB_WEB_Angular | #42 | US: Store Category wise Medicine Category mapping to display in POS | Open | Tushar Prajapati | Get more understanding for the task from Mayur sir | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zeelab/zeelab_web_angular/-/issues/42
4 | Goal_digger_220224[.NET] | cpos_web_angular | #749 | Issue : Warehouse Stock is displaying wrong in Order & Stock Assessment report | Doing | Tushar Prajapati | I need help, Vishal Sir. The Odoo to CPOS Odoo Warehouse Stock sync is not working. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/749
5 | Goal_digger_070324[.NET] | ZOTA_CPOS | #42 | US: Store Category wise Medicine Category mapping to display in POS | Open | Tushar Prajapati | Get more understanding for the task from Mayur sir | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zeelab/zeelab_web_angular/-/issues/42
5 | Goal_digger_070324[.NET] | ZOTA_CPOS | #708 | Issue : Displaying error message for single day, Single store searching for product wise sales return without tax report in live | Doing | Nidhi garala | till not getting root cause | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/708
6 | Goal_digger_070324[.NET] | ZOTA_CPOS | #723 | Issue: Export button is not working in reports for data output in excel | QA | Nidhi garala | Merge req.pending | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/723
7 | Goal_digger_070324[.NET] | ZOTA_CPOS | #738 | Issue: Demand Vs Supply Report - Data blank issue for the supply from stockiest to retailer details | QA | Nidhi garala | depended task | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/738
8 | Goal_digger_070324[.NET] | ZOTA_CPOS | #733 | Issue: First billing date & Live date sync issue for CPOS & Odoo | Doing | Pankaj Motwani | Need to compare latest data as per excel by Divyesh | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota-pos-framework/-/issues/733
1 | Goal_digger_210324[.NET | Kendriya Bhandar Grocery Pos_framework | #1 | US: Kendriya Bhandar (Grocery) - Theme implementation | QA | nilesh patel | Development is Done Pending For CPOS. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/kendriya-bhandar/grocery/pos_framework/-/issues/1
2 | Goal_digger_210324[.NET | Kendriya Bhandar Grocery Cpos_web_angular | #1 | US: Kendriya Bhandar (Grocery) - Theme implementation & Hosting | QA | nilesh patel | Development is Done from our side but hosting API is provided on 03-04-2024. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/kendriya-bhandar/grocery/cpos_web_angular/-/issues/1
3 | Goal_digger_210324[.NET | ZOTA_CPOS | #771 | Issue : Demand Vs Supply Report (Secondary) Total Invoice Price and POS Sales Invoice Total Price (Without tax) are Mismatch | QA | Nidhi garala | Analysis is done there is issue in sync cycle for poheader update, so once quick update wii give to customer and resync poheader data then this issue will be resolved.
4 | Goal_digger_210324[.NET | ZOTA_CPOS | #708 | Issue : Displaying error message for single day, Single store searching for product wise sales return without tax report in live | QA | Nidhi garala | Need to help from person who has zota cpos live data base rights for cheking
5 | Goal_digger_210324[.NET | ZOTA_CPOS | #775 | Issue: First Billing date is displaying blank for Store Code CMHMUM0315 in Live | Open | Pankaj Motwani | As, Need to check at customer end why odoo sync didn't worked and currently customer is not picking up call to provide us screen But, once customer provide us anydesk will resolve issue instantly | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/775
6 | Goal_digger_210324[.NET | ZOTA_CPOS | #730 | Issue: Closing date is displaying different in Store stock report | Doing | Pankaj Motwani | Identified issue and once quick update is applied at customer end then issue will be resolved also attached query which will enhance performace depending on conditons | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/730
7 | Goal_digger_210324[.NET | Kendriya Bhandar Grocery Cpos_web_angular | #2 | Pos Sales Invoice : Add Request Report button | QA | nilesh patel | This task Assignee 01-04-2024 and other prioritie task is running. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/kendriya-bhandar/pharma/cpos_web_angular/-/issues/2
8 | Goal_digger_210324[.NET | Kendriya Bhandar Pharma Cpos_web_angular | #2 | Pos Sales Invoice : Add Request Report button | QA | nilesh patel | This task Assignee 01-04-2024 and other prioritie task is running. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/kendriya-bhandar/grocery/cpos_web_angular/-/issues/2
9 | Goal_digger_210324[.NET | B2B | #20 | US: Admin: Scheme Master: Scheme Detail: Material: Discount% | Open | Nitish Kumar Singh | This task is Carryforward for next because I am busy in another task which is high priority than this Task | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/b2b_admin_portal/-/issues/20#top
| Goal_digger_210324[.NET | B2B | #25 | US: Admin: Scheme Master: Scheme Detail: Material: Item Quantity Discount% | OPen | Nitish Kumar Singh | This task is Carryforward for next because I am busy in another task which is high priority than this Task | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/b2b_admin_portal/-/issues/25
1 | Goal_digger_040424[.NET] | ZOTA_CPOS | #772 | US: CPOS: Master: Store List: Need to Add New Field Name as "SBN (Store Branch Name)" | QA | Tushar Prajapati | Development is Done from our side but getting error from odoo side. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/772
2 | Goal_digger_040424[.NET] | Zota_Dpos_Framework | #32 | US: DPOS user (Stockiest/Vendor/CNF) wise Product Master mapping | Doing | Tushar Prajapati | Due to ZOTA DPOS release Not able to complete this task, So need to carry forward this task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota_dpos/-/issues/23
3 | Goal_digger_040424[.NET] | CPOS_WEB_Angular | #760 | Issue: Data Mismatch in Store Stock report | QA | nilesh patel | Due to ZOTA DPOS release Not able to complete this task, So need to carry forward this task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/760
4 | Goal_digger_040424[.NET] | Zota_cPOS | #711 | US: Store Purchase - Time need to display with "PO Approve Date Time" & "PO Sync Date Time" | QA | Nidhi | developing is done but Testing is pending due to some health issue, as need to carry forward this task
5 | Goal_digger_040424[.NET] | Zota_cPOS | #771 | Issue : Demand Vs Supply Report (Secondary) Total Invoice Price and POS Sales Invoice Total Price (Without tax) are Mismatch | QA | Nidhi | Analysis is done there is issue in sync cycle for poheader update, so once quick update wii give to customer and resync poheader data then this issue will be resolved.
6 | Goal_digger_040424[.NET] | Zota_cPOS | #777 | Issue: Batch wise Sale Tertiary Report - Data output issue for category mismatch (DAVAINDIA NON EXCLUSIVE) | QA | Nidhi | i had tested this scenario multiple times on live server , but does not got any data mismatch issue , may be due to some network down issue , this issue would be generated. so i m giving to QA for more analysis. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/777
7 | Goal_digger_040424[.NET] | Zota_cPOS | #751 | US: Zota Report: Sales Summary Report | QA | Nidhi | due to emergency leave developing was completed on 16/04/2024 and Giving to QA after this day | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/751
8 | s | Zota_cPOS | #273 | Issue : CPOS - store code : CMHJAL0018- Master Report - Product wise sales | open | Nidhi | Due to emergency leave not able to develop | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/273
1 | Goal_digger_180424[.NET] | ZOTA_cPOS | #766 | Issue: POS : P.code : 3534 expiry showing wrong | Open | Pankaj Motwani | As, it's assigned recently and didn't got time to take this task due to issue of e-way bill not able to generated on linux server | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota-pos-framework/-/issues/766
2 | Goal_digger_180424[.NET] | ZOTA_cPOS | #730 | Issue: Closing date is displaying different in Store stock report | On Hold | Pankaj Motwani | As, I have done working for same but once new data gets sync on live then will be able to check | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/730
3 | Goal_digger_180424[.NET] | BPPI_POS | #625 | Issue:- LS00050 :-E Way Bill not Generate On Portal | Doing | Pankaj Motwani | As, trying to find out issue for linux server but not able to find issue for same | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/bppi/pos_dotnet/-/issues/625
4 | Goal_digger_180424[.NET] | GujcoMart | #2 | Issue 2: Product doesn't load while creating purchase invoice | Doing | Nibha Tyagi | need to revert the functionality due to unclear understanding | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/gujcomart/pos_framework/-/issues/2
1 | Goal_digger_180424[.NET] | ZOTA_POS | #607 | US: Bill value based Scheme Discount Amount calculation will be before tax & Need to display line item wise | Open | Pankaj Motwani | As, we don't need to take this task as talk betweeen paresh and deval bhi has com | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota-pos-framework/-/issues/607
2 | Goal_digger_180424[.NET] | ZOTA_POS | #730 | Issue: Closing date is displaying different in Store stock report | On Hold | Pankaj Motwani | As, we don't need to take this task as talk betweeen paresh and deval bhi has com | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/730
5 | Goal_digger_180424[.NET] | Zota_cPOS | #1 | US: Zota Report: Sales Summary Report | QA | Nidhi Garala | Developing is done ,when Zota cpos environment will be ready this task will be merged into that latest project and then given in to QA. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota_cpos_web_angular/-/issues/1
6 | Goal_digger_180424[.NET] | Zota_cPOS | #2 | US: Zota Report: Sales Dump Report | QA | Nidhi Garala | Developing is done ,when Zota cpos environment will be ready this task will be merged into that latest project and then given in to QA. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota_cpos_web_angular/-/issues/2
7 | Goal_digger_180424[.NET] | Zota_cPOS | #3 | US: Zota Report: Sales Return Report | QA | Nidhi Garala | Developing is done ,when Zota cpos environment will be ready this task will be merged into that latest project and then given in to QA. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota_cpos_web_angular/-/issues/3
8 | Goal_digger_180424[.NET] | cPOS | #771 | Issue : Demand Vs Supply Report (Secondary) Total Invoice Price and POS Sales Invoice Total Price (Without tax) are Mismatch | QA | Nidhi Garala | this task need to carryforward because Analysis is done there is issue in sync cycle for poheader update, so once quick update wii give to customer and resync poheader data then this issue will be resolved. for this discuss with paresh bhai and pankaj bhai is pending. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/771
1 | Goal_digger_020524[.NET] | ZOTA_POS | #764 | US: Sales Invoice - At a time only one scheme type will be applicable for single sales invoice | On Hold | Pankaj Motwani | As, discussion related to scheme functionality is done with client but client has not given conformation related to same task | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota-pos-framework/-/issues/764
2 | Goal_digger_020524[.NET] | ZOTA_POS | #607 | US: Bill value based Scheme Discount Amount calculation will be before tax & Need to display line item wise | On Hold | Pankaj Motwani | As, discussion related to scheme functionality is done with client but client has not given conformation related to same task | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota-pos-framework/-/issues/607
3 | Goal_digger_020524[.NET] | ZOTA_CPOS | #730 | Issue: Closing date is displaying different in Store stock report | On Hold | Pankaj Motwani | Until and unless POS data is not getting sync properly we will not able to check | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/730
4 | Goal_digger_020524[.NET] | ZOTA_CPOS | #795 | Auto selection of new store in Terms & condition form | Doing | Tushar Prajapati | This task Assignee yesterday(14-05-2024). | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/795
5 | Goal_digger_020524[.NET] | GujCoMart_POS | #2 | US: Purchase Invoice - Direct PI & Local PI | Open | Nibha Tyagi | the development is pending from odoo side that's why unable to get sales Invoice against PO from HO | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/gujcomart/pos_framework/-/issues/2
6 | Goal_digger_020524[.NET] | Zota_Dpos | #6 | US: Zota Report: Purchase Return Report | QA | Nidhi Garala | Devloping is done but unit testing is incomplete due to DPOS to Cpos to Odoo cycle was not working properly.
7 | Goal_digger_020524[.NET] | Zota_Dpos | #7 | US: Zota Report: Stock Report | Doing | Nidhi Garala | Developig is continue due to stuck in req. report functionality in purchase reports , so more tims was spend on that report.
8 | Goal_digger_020524[.NET] | Zota_Dpos | #5 | US : Zota Report :Purchase Order Dump Report | Open | Nidhi Garala | Yesterday US was changed so need to reworkon this report , this report is working fine as previous US .
1 | Goal_digger_160524[.NET] | DavaIndia_CPOS | #807 | US: Dropdown with multiple selection required in Advance filter | Doing | Tushar Prajapati | I have been stuck in Odoo for the CPOS Sync task for 3 days, and this task is lengthy, so I cannot complete it. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/807
2 | Goal_digger_160524[.NET] | DavaIndia_POS | #774 | E-Invoice functionality at DPOS & POS for B2B invoices | Doing | Pankaj Motwani | Due to another task taken in between related to coco store need to configure other item than davaIndia #785 | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota-pos-framework/-/issues/774
3 | Goal_digger_160524[.NET] | Zota_CPOS | #6 | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/zota_dpos/zota_cpos_web_angular/-/issues/6 | QA | Nidhi Garala | This report is working fine on davaindia staging but on Zoat enviorment syncing from odoo to Zota staging is not working. so not able to test on Zota Staging.
4 | Goal_digger_160524[.NET] | DavaIndia_cpos | #771 | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos_web_angular/-/issues/771 | Doing | Nidhi Garala | i does not getting route cause for this task , need some ones help for resloving , so need to carry forward.
https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/b2b_admin_portal/-/issues/25
1 | Goal_digger_160524[.NET] Zota_B2B_AdminPannel |  | #25 | US: Admin: Scheme Master: Scheme Detail: Material: Item Quantity Discount% | Doing | Nitish Kumar Singh | This task has been carry forward for next milesstone cause of , I have another task from Ekatva which is high priority than current task. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/b2b_admin_portal/-/issues/20
2 | Goal_digger_160524[.NET] Zota_B2B_AdminPannel |  | #20 | US: Admin: Scheme Master: Scheme Detail: Material: Discount% | Doing | Nitish Kumar Singh | This task has been carry forward for next milesstone cause of , I have another task from Ekatva which is high priority than current task.
1 | Goal_digger_130624[.NET] | DavaIndia POS | #779 | US: Integration of Paytm machine with POS for Payment using card swipe & QR code scan | Doing | Pankaj Motwani | Stuck related to functionality for saving discarded or cancelled against particular invoice number | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/pos/zota-pos-framework/-/issues/779
2 | Goal_digger_130624[.NET] | Zota Vendor Portal | #82 | Issue: Multiple Pack size search field is displaying in Purchase Order list in Staging and Live | Pending | Pankaj Motwani | As, I was working on issue related to paytm integration. So, didn't got time for same. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/vendor-portal/vendorportal_web_angular/-/issues/82
3 | Goal_digger_130624[.NET] | Zota Vendor Portal | #83 | Issue : Displaying Invalid Input while searching with PO number in ASN List Page in Staging and Live | Pending | Pankaj Motwani | As, I was working on issue related to paytm integration. So, didn't got time for same. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/vendor-portal/vendorportal_web_angular/-/issues/83
4 | Goal_digger_130624[.NET] | DavaIndia cPOS | #837 | US: CPOS: Add missing columns (State, Store Category & Store Code) in several reports - Part - 1 | Doing | Nidhi Garala | Needs to carry forward As i was stuck in one common issue in csv file generation
1 | Goal_digger_270624[.NET] | DavaIndia_CPOS | #852 | US : SSRS REPORT : GST REPORTS Required for all category | Doing | Tushar Prajapati | Development is done, but we are getting issues from the client-side database. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos/cpos_web_angular/-/issues/852
1 | Goal_digger_110724[.NET] | DavaIndia_POS | #779 | US: Integration of Paytm machine with POS for Payment using card swipe & QR code scan | Doing | Pankaj Motwani | Due to change and scenario encountered in paytm functionality. When scenario encountered discussed with paresh bhai and worked on particular development for same | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/pos/zota-pos-framework/-/issues/779
1 | Goal_digger_031024[.NET] | DavaIndia CPOS | #956 | US: CPOS: Store-Wise Total Allocated and Utilized Petty Cash Report | Doing | Pankaj Motwani | As, product backlog performed on 16/10/2024 one day before milestone date. So, need to carry forward this task to next milestone | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos/cpos_web_angular/-/issues/956
1 | Goal_digger_171024 [.Net] | CPOS_WEB_Angular | #982 | US : Improvement : Update table joins to use id columns for all sync queries | Doing | Pankaj Motwani | Due to other task like took in between which was priority like GujcoMart | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/cpos/cpos_web_angular/-/issues/982
1 | Goal_digger_171024 [.Net] | DavaIndia POS | #591 | US: POS: Batch wise scheme apply in Sales invoice scheme (Discount % on Material) | open | Tushar Prajapati | Changes in #893 and support tasks have impacted the timeline, so this task will be Carry Forward to the next milestone. | https://code.ethicsinfotech.in/ethics-projects/ethics-net-backend/zota/pos/zota-pos-framework/-/issues/591

## MilestoneUnplannedTask
SRNo | Milestone | Project | TaskId | TaskName | Task Status | Assigned By | Assigned To
1 | Goal_digger_270723[.NET] | zota-pos-framework | 540 | US: DPOS Sales Invoice - Sales Preferences (Line Item Discount) | Doing | Deval | Nidhi Garala
2 | Goal_digger_270723[.NET] | CPOS_WEB_Angular | 453 | Issue: Stock Return > Batch Recall : The product is not showing in the batch recall report. | RFR | Ajay | Pankaj Motwani
3 | Goal_digger_270723[.NET] | zota-pos-framework | 534 | Object reference error message is displaying after closing Sales Invoice retail Window | RFR | Nilesh | Mayur Prajapati
4 | Goal_digger_270723[.NET] | CPOS_WEB_Angular | 272 | New module for Request based Reports (Stock --> Store Stock) export to excel functionality | RFR | Deval | Pankaj Motwani
5 | Goal_digger_270723[.NET] | CPOS_WEB_Angular | 442 | Requested Report : Report Name/Request Date Time column is not displaying in Requested report page | RFR | Nilesh | Amruta Salvi
6 | Goal_digger_270723[.NET] | CPOS_WEB_Angular | 438 | Disapprove functionality is not working properly in Account details and Dispatch details in store execution process | RFR | Nilesh | Amruta Salvi
7 | Goal_digger_270723[.NET] | VendorPortal_WEB_Angular | 51 | Expiry Date Logic need to be change. | RFR | Akash Rana | Amruta Salvi
1 | Goal_digger_100823[.NET] | B2B_Admin_Portal | 175 | Suggestion: Banner List_Advance Filter >> 'Publish Status' Field - Unpublish option should be selected in drop-down after Reset button is applied | RFR and Closed | Roshni | Rutva
2 | Goal_digger_100823[.NET] | zota-pos-framework | 554 | Error message is displaying after copy to sales invoice from Quotation in DPOS | RFR | Nilesh | Tushar
3 | Goal_digger_100823[.NET] | CPOS_WEB_Angular | 456 | Drug license challan and Marketing Material challan date showing wrong in Live for Store Execution Tracker | RFR | Nilesh | Amruta Salvi
4 | Goal_digger_100823[.NET] | CPOS_WEB_Angular | 457 | Store is not sync in odoo after agreement | RFR | Nilesh | Amruta Salvi
5 | Goal_digger_100823[.NET] | B2B_API_DotNetCore | 43 | US: API: Admin: Store Management: Registration Approval: Detail Page | Doing | Hasmuk Sir | Viraj Pansara
6 | Goal_digger_100823[.NET] | zota-pos-framework | 565 | US: Debit Note against Batch Recall Policy from CPOS | QA | Deval | Tushar Prajapti
7 | Goal_digger_100823[.NET] | zota-pos-framework | 568 | Issue : Stock Adjustment Sr no is reflection wrong after Stock Adjustment | RFR | Nilesh | Nidhi
1 | Goal_digger_240823[.NET] |  | 575 | Regression Testing: Release - POS (v1.41.0) |  | Rutva | Nilesh
2 | Goal_digger_240823[.NET] | VendorPortal_WEB_Angular | 54 | Issue : Error message is displaying while Barcode Generation | RFR | Nilesh | Amruta Salvi
3 | Goal_digger_240823[.NET] | CPOS_WEB_Angular | 481 | Issue : Return Policy : From Date is greater than To date for specific return | RFR | Nilesh | Pankaj Motwani
4 | Goal_digger_240823[.NET] | CPOS_WEB_Angular | 479 | Issue : Batch Recall Edit functionality is not working | RFR | Nilesh | Amruta Salvi
5 | Goal_digger_240823[.NET] | CPOS_WEB_Angular | 482 | Issue : validation message is displaying wrong before edit return policy before 2 days | RFR | Nilesh | Nidhi
6 | Goal_digger_240823[.NET] | VendorPortal_WEB_Angular | 55 | Issue :Batch selection dropdown is not open if product have multiple batch while making ASN | RFR | Nilesh | Neelam
7 | Goal_digger_240823[.NET] | VendorPortal_WEB_Angular | 57 | Issue : History Pop is displaying after session time out in Delivery planning | RFR | Nilesh | Ashish kumar
1 | Goal_digger_080923[.NET] | CPOS_WEB_Angular | 506 | Issue: Some Store type is not displaying in Advance search in Scheme Report | RFR | Nilesh | Amruta Salvi
2 | Goal_digger_080923[.NET] | CPOS_WEB_Angular | 505 | Issue: Scheme Report Filter page is displaying after session time out | RFR | Nilesh | Ashish
3 | Goal_digger_080923[.NET] | CPOS_WEB_Angular | 502 | Issue: Column is displaying in grid if it is un tick in Show/Hide Column | RFR | Nilesh | Ashish
4 | Goal_digger_080923[.NET] | CPOS_WEB_Angular | 501 | Regression | RFR | Rutva | Nilesh
5 | Goal_digger_080923[.NET] | zota-pos-framework | 598 | Regression | RFR | Rutva | Nilesh
6 | Goal_digger_080923[.NET] | CPOS_WEB_Angular | 508 | Issue: State selection is removed after edit T&C and select all State | RFR | Nilesh | Tushar
7 | Goal_digger_080923[.NET] | CPOS_WEB_Angular | 528 | Issue: MB not displaying after file size in Notification master add page | RFR | Nilesh | Tushar
1 | Goal_digger_210923[.NET] | CPOS_WEB_Angular | 531 | Issue : Extra column is displaying in Terms and Condition List page in Live | RFR | Nilesh | Amruta Salvi
2 | Goal_digger_210923[.NET] | B2B Admin Panel | #1 | US: Admin: Item Master: Item Listing Page
3 | Goal_digger_210923[.NET] | B2B Admin Panel | #6 | US: Admin: Item Master: Item Detail Page: Rate: Rate Slab Form
4 | Goal_digger_210923[.NET] | B2B Admin Panel | #9 | US: Admin: Item Master: Item Detail Page: Catalogue
5 | Goal_digger_210923[.NET] | B2B Admin Panel | #201 | Issue : Advanced Filter - 'Publish Status' has displayed value 'All' by it's own even there is filter for Published data | RFR | Rutva | Viraj Pansara
6 | Goal_digger_210923[.NET] | B2B Admin Panel | #192 | Issue : Edit Banner >> Level Selection - Loader action has started when user tries to insert some data in Searchbox and Press Enter | RFR | Hiral Thakkar | Viraj Pansara
7 | Goal_digger_210923[.NET] | CPOS_WEB_Angular | #536 | Regression |  | Rutva | Nilesh
8 | Goal_digger_210923[.NET] | zota-pos-framework | #619 | Regression |  | Rutva | Nilesh
9 | Goal_digger_210923[.NET] | B2B Admin Panel | #225 | suggestion: Buttons is image section looking disable. |  | Deepak Pant | Viraj Pansara
1 | Goal_digger_051023[.NET] | B2B Admin Panel | #2 | US: Admin: Item Master: Item Detail Page: Basic Information |  | Hasmukh sir | Deepak Pant
2 | Goal_digger_051023[.NET] | B2B Admin Panel | #8 | US: Admin: Item Master: Item Detail Page: Promocode |  | Hasmukh sir | Deepak Pant
3 | Goal_digger_051023[.NET] | B2B Admin Panel | #12 | US: Admin: Item Master: Item Detail Page: Rate: Margin Table | RFR | Hasmukh sir | Deepak Pant
4 | Goal_digger_051023[.NET] | B2B Admin Panel | #8 | US: Admin: Item Master: Item Detail Page: Promocode
5 | Goal_digger_051023[.NET] | CPOS_WEB_Angular | #547 | Issue: GST Word is not displaying in Capital latter in all GST Reports | RFR | Nilesh | Tushar
6 | Goal_digger_051023[.NET] | zota-pos-framework | #647 | Suggestion: Update Validation message from 48 to 168 hrs (7 days) while saving Purchase invoice in POS and DPOS to make Debit note | RFR | Nilesh | Tushar
1 | Goal_digger_191023[.NET] | B2B Admin Panel | #17 | US: Admin: Catalogue Master: Catalogue Item Mapping Page |  | Viraj | VIraj
2 | Goal_digger_191023[.NET] | B2B Admin Panel | #32 | US: Admin: Deals & Offer Master: List Page |  | Nitish
3 | Goal_digger_191023[.NET] | CPOS_WEB_Angular | #571 | US : GST Reports in SSRS Report | QA | Paresh Patel | Tushar Prajapati
1 | Goal_digger_021123[.NET] | B2B Admin Panel | #173 | Suggestion: Banner List_Advance Filter >> 'Publish Status' & 'Catalogue Attached' Drop-down option should not display as selected when mouse hover is removed | RFR | Hiral | Dipak Pant
2 | Goal_digger_021123[.NET] | B2B Admin Panel | #185 | Suggestion: Add Banner >> Validation message needs to change for 'Seller Name' Field | RFR | Hiral | Dipak Pant
3 | Goal_digger_021123[.NET] | CPOS_WEB_Angular | #573 | Issue: Scheme master #218 : Free Material is edited within 2 days from today's date | QA | Pankaj Motwani | Nilesh Patel
4 | Goal_digger_021123[.NET] | CPOS_WEB_Angular | #587 | US: Need to display all column wise contents with wrap text facility to display all columns in History pop-up window | RFR | Pankaj Motwani | Nilesh Patel
5 | Goal_digger_021123[.NET] | Transport Portal | #10 | Need to show Order No which was not working | RFR | Pankaj Motwani | Nilesh Patel
6 | Goal_digger_021123[.NET] | VendorPortal_WEB_Angular | #61 | Issue : Expiry date is displaying after click on save button while generating ASN if Manufacturing and Expiry date both are blank | RFR | Nilesh | Tushar
7 | Goal_digger_021123[.NET] | VendorPortal_WEB_Angular | #62 | Issue : Error message is displaying while Generating Barcode | RFR | Nilesh | Pankaj Motwani
8 | Goal_digger_021123[.NET] | Transport Portal | #11 | Suggestion: Need to order No field in search field and Advance search | QA | Pankaj Motwani | Nilesh Patel
1 | Goal_digger_211123[.NET] | B2B Admin Panel | #259 | Issue: Homepage mobile: the banner/slider/list,etc..not displaying in mobile application when publish level set as District. | RFR | Deepak | Deepak Pant
2 | Goal_digger_211123[.NET] | B2B Admin Panel | #190 | Suggestion: Catalogue Product Mapping | RFR | Viraj Pansara | Deepak Pant
3 | Goal_digger_211123[.NET] | B2B Admin Panel | #38 | US: Admin: Home Page Mobile: List Page | RFR | Nitish Kumar | Deepak Pant
1 | Goal_digger_301123[.NET] | B2B Admin Panel | #53 | US: Admin: Mobile Home Page: Detail Page: Section Details | RFR | Nitish kumar | Deepak Pant
2 | Goal_digger_301123[.NET] | B2B Admin Panel | #33 | US: Admin: Deals & Offer Master: Detail Page | RFR | Nitish kumar | Deepak Pant
3 | Goal_digger_301123[.NET] | B2B Admin Panel | #7 | US: Admin: Item Master: Item Detail Page: Category | RFR | Nitish kumar | Deepak Pant
1 | Goal_digger_141223[.NET] | B2B Admin Panel | #39 | US: Admin: Home Page Mobile: Detail Page: Basic Information | RFR | Nitish kumar | Deepak Pant
2 | Goal_digger_141223[.NET] | B2B Admin Panel | #106 | US: Admin: Notification Master: Notification Detail: Basic Information |  | Nitish kumar | Deepak Pant
1 | Goal_digger_210324[.NET | Kendriya Bhandar Grocery Cpos_web_angular | #2 | Pos Sales Invoice : Add Request Report button | QA | Tushar | Nilesh
2 | Goal_digger_210324[.NET | Kendriya Bhandar Pharma Cpos_web_angular | #2 | Pos Sales Invoice : Add Request Report button | QA | Tushar | Nilesh
3 | Goal_digger_210324[.NET | CPOS_WEB_Angular | #776 | Pos Sales Invoice : Add Request Report button | RFR | Tushar | Nilesh
4 | Goal_digger_210324[.NET | ZOTA_CPOS | #773 | Issue: Scheme Reports Export button is not working | RFR | Nilesh | Nidhi Garala
5 | Goal_digger_210324[.NET | ZOTA_CPOS | #770 | Issue : Zota Store is displaying in Store Stock report | RFR | Nilesh | Amruta Salvi
1 | Goal_digger_160524[.NET] | ZOTA_POS | 785 | US: Other products creation & sales requirement for COCO store "CUPNOI0324" | QA | Pankaj | Deval